## Sheet1
Stakeholder Map (Sample)
Category | Target Stakeholder(s) | Level of influence | Level of interest | Purpose | Format | Frequency and/or timeframe | Responsibility | Budget ($)
Internal | Project Sponsor | High | High | Progress; buy-in | Meeting; Project Manager to prepare agenda and update Action Plan in readiness for this meeting | Weekly | Project Manager | N/a
External - government | Customer | High | High | Progress; buy-in; input into deliverables; acceptance of deliverables | Meetings; emails | As needed | Project Manager | $low
Internal | Project Team | Low-Med | High | Project Team meeting | Meeting; Project Manager to prepare agenda and update Action Plan in readiness for this meeting | Fortnightly | Project Manager | N/a
Internal | Project Board | High | High | Progress; submission of deliverables; lodgement of change requests & exception reports | Project Status Report; Request for Change; Exception Report | Monthly; as needed | Project Manager | N/a
Internal | Corporate Executive | High | Medium | Sign-off at identified milestones | Briefing notes; meeting attendance | As required | Project Sponsor | N/a
Internal | Interested staff | Low | High | Informal progress update; sharing of templates & learnings | Meeting | Weekly | Coordinator, PMO | N/a